## Instructions
Project Tracker Instructions
Use Employee_Master for employees and Task_Tracker for all task entry. Monthly tabs show due tasks by month and auto-display carry-forward open tasks from earlier months.
Workflow
1. Add or update employees in Employee_Master.
2. Add or edit tasks only in Task_Tracker.
3. Due Date controls the month-wise reporting tabs.
4. Any task not marked Completed or Cancelled before a later month will appear in Carry Forward for that month.
5. Use Monthly_Report_Summary for month-wise totals and employee report tabs for individual performance.
Editable areas
Unlocked input cells are available in Employee_Master, Task_Tracker, and B4/B5 on the general Employee_Report.
Protection password
TaskLock2026!
Reporting logic
Tasks Due This Month = tasks with Due Date inside the month. | User input
Completed = tasks in that month bucket with Status = Completed. | Auto-calculated / locked
Carry Forward = tasks with Due Date before the month start that are still not Completed/Cancelled. | Linked from another sheet
Hours are summarized from the task-level Actual Hours field. | Overdue or attention needed
Dark blue bars | Section headers / KPI blocks
Latest updates
- Employee names now come from Employee_Master: Pammi Gaur and Pankaj Vairagade.
- Use Task_Tracker column AA for Source. Manager, report status, and linked step IDs are auto-filled.
- Use Task_Steps Parent Task ID dropdown to map each step back to the Task_Tracker.
- Employee and manager reports now pull directly from Task_Tracker and Task_Steps.

## Dashboard
Dashboard
Dashboard summary of project delivery. Use Monthly_Report_Summary and month tabs for month-wise reporting.
Selected Month | All
Total Tasks |  |  | Open Tasks |  | Completed |  | Overdue
Estimated Hours |  |  | Actual Hours |  | Hours Variance |  | Completion Rate
12-month trend |  |  |  | Status summary |  | Employee workload snapshot
Month | Tasks Due | Completed | Actual Hours | Status | Count | Employee | Tasks | Actual Hrs | Overdue
2026-04 |  |  |  | Not Started
2026-05 |  |  |  | In Progress
2026-06 |  |  |  | Review
2026-07 |  |  |  | On Hold
2026-08 |  |  |  | Blocked
2026-09 |  |  |  | Completed
2026-10 |  |  |  | Cancelled
2026-11
2026-12
2027-01
2027-02
2027-03
See Employee_Summary for the full employee list and more detailed metrics.

## Monthly_Report_Summary
Monthly Reporting Summary
This sheet gives month-wise totals for all tasks and both employees. Enter or edit tasks in Task_Tracker; reports update automatically.
Month Start | Month | Total Due | Completed | Carry Forward | Actual Hrs | Open in Bucket
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Use the monthly tabs for task-by-task detail and carry-forward lines.

## Employee_Master
Employee Master
Add each employee once. Task assignments and reports use this sheet as the source list.
Emp ID | Employee Name | Department | Role | Manager | Email | Join Date | Weekly Capacity (hrs) | Status | Location | Notes
| Pammi Gaur | Operations | Project Coordinator | Sara Khan | pammi.gaur@company.com | 2025-07-15 | 40 | Active | Remote | Owns operations execution, follow-ups, and client coordination.
| Pankaj Vairagade | Business Systems | Business Analyst | Sara Khan | pankaj.vairagade@company.com | 2024-11-04 | 40 | Active | Bengaluru | Handles reporting, audit prep, and process improvement work.
Note on B5: Enter the employee name exactly as you want it to appear in task assignment dropdowns.
Note on H5: Typical weekly working capacity in hours (for workload analysis).

## Task_Tracker
Monthly Task Upload & Master Tracker
Enter or edit all tasks here. Due Date drives the month-wise reporting tabs. Source, manager report status, and linked step IDs update automatically.
Task ID | Project | Program | Task Title | Task Description | Assigned To | Department | Priority | Status | Action Type | Planned Start | Due Date | Completed Date | Est. Hours | Actual Hours | Hours Variance | Days Open | Overdue Flag | Month Bucket | Progress % | Next Step | Created Date | On-Time Close | Step Count | Step Completion % | Task Notes | Source | Manager | Manager Report | Linked Step IDs | Open Step Count | Project Key
| Customer Onboarding Revamp | Implementation | Collect client requirements | Gather and confirm onboarding requirements with the client and internal operations team. | Pammi Gaur |  | High | Completed |  | 2026-04-01 | 2026-04-05 | 2026-04-04 | 12 | 11 | [5 empty] | Archive signed scope and handoff to execution. | 2026-03-31 |  |  |  | Closed one day before deadline. | Client Request
| Customer Onboarding Revamp | Implementation | Build onboarding checklist | Create the master checklist used for onboarding execution and internal QA. | Pammi Gaur |  | High | In Progress |  | 2026-04-06 | 2026-04-12 |  | 10 | 6 | [5 empty] | Finalize version 2 after operations review. | 2026-04-05 |  |  |  | Core delivery task for current week. | Operations Review
| Customer Onboarding Revamp | Training | Schedule client training sessions | Coordinate training slots, attendees, and agenda for rollout. | Pammi Gaur |  | Medium | Review |  | 2026-04-08 | 2026-04-14 |  | 8 | 7 | [5 empty] | Await leadership approval for final schedule. | 2026-04-07 |  |  |  | Content ready; waiting on confirmation. | Leadership Follow-up
| Website Migration | Operations | Vendor coordination for content freeze | Lock the final website content set and confirm the vendor freeze date. | Pammi Gaur |  | Critical | Blocked |  | 2026-04-03 | 2026-04-08 |  | 6 | 3 | [5 empty] | Need vendor approval to proceed. | 2026-04-02 |  |  |  | Blocked by external dependency; now overdue. | Vendor Dependency
| Customer Portal Launch | Go-Live | Prepare launch readiness checklist | Prepare pre-launch readiness checks and stakeholder signoffs. | Pammi Gaur |  | High | Not Started |  | 2026-05-01 | 2026-05-08 |  | 7 | [6 empty] | Kick off launch checklist in May. | 2026-04-09 |  |  |  | Upcoming task already planned. | Program Plan
| Website Migration | Analytics | Set up UAT defect log | Create the testing log and owner matrix for website UAT. | Pankaj Vairagade |  | High | Completed |  | 2026-04-02 | 2026-04-07 | 2026-04-07 | 9 | 10 | [5 empty] | Share closure summary with stakeholders. | 2026-04-01 |  |  |  | Completed on time with slight overrun. | Audit Request
| Website Migration | Reporting | Create weekly progress dashboard | Build the weekly dashboard showing delivery, defects, and risks. | Pankaj Vairagade |  | Critical | In Progress |  | 2026-04-05 | 2026-04-15 |  | 14 | 9 | [5 empty] | Add leadership metrics and QA final formulas. | 2026-04-04 |  |  |  | High-visibility reporting deliverable. | Internal Compliance
| Q2 Compliance Audit | Documentation | Compile policy evidence pack | Collect policies, approvals, and evidence files for audit review. | Pankaj Vairagade |  | Critical | On Hold |  | 2026-04-04 | 2026-04-10 |  | 16 | 5 | [5 empty] | Waiting for legal documents before pack can be completed. | 2026-04-03 |  |  |  | Paused pending legal input. | System Improvement
| Q2 Compliance Audit | Automation | Automate control checklist | Turn the manual compliance checklist into a reusable controlled template. | Pankaj Vairagade |  | Medium | Not Started |  | 2026-04-11 | 2026-04-22 |  | 18 | [6 empty] | Kick off automation design with IT. | 2026-04-09 |  |  |  | Planned for later this month. | Management Review
| Process Excellence | Reporting | Monthly KPI workbook cleanup | Clean tabs, formulas, and broken links in the KPI workbook. | Pankaj Vairagade |  | Low | Completed |  | 2026-03-24 | 2026-03-29 | 2026-03-28 | 5 | 4 | [5 empty] | Archive previous version and publish final file. | 2026-03-23 |  |  |  | Closed early with clean handoff. | Recurring Reporting
| Customer Portal Launch | UAT | Complete UAT signoff pack | Compile test evidence, approvals, and release notes for signoff. | Pammi Gaur |  | High | Completed |  | 2026-05-09 | 2026-05-20 | 2026-05-19 | 8 | 9 | [5 empty] | Share the final signoff pack with the sponsor team. | 2026-05-08 |  |  |  | Completed one day early with minor extra effort. | Client Escalation
| Vendor Migration | Planning | Finalize migration cutover checklist | Prepare the final cutover checklist covering owners, timings, and rollback plan. | Pammi Gaur |  | Critical | In Progress |  | 2026-06-01 | 2026-06-06 |  | 10 | 4 | [5 empty] | Collect final approvals from infra and vendor teams. | 2026-05-29 |  |  |  | Key June deliverable now in progress. | Change Request
| Q2 Compliance Audit | Reporting | Prepare audit dashboard pack | Create management-facing dashboard pack for the internal audit review. | Pankaj Vairagade |  | High | Review |  | 2026-05-14 | 2026-05-25 |  | 11 | 10 | [5 empty] | Incorporate reviewer comments and freeze final charts. | 2026-05-13 |  |  |  | Draft prepared and under review. | Finance Audit
| Process Excellence | Documentation | Publish SOP version 2 | Update the SOP document with revised controls, examples, and approval history. | Pankaj Vairagade |  | Medium | Not Started |  | 2026-06-03 | 2026-06-10 |  | 12 | [6 empty] | Kick off the draft update and collect stakeholder comments. | 2026-06-01 |  |  |  | Planned June documentation task. | Monthly Review
| Customer Portal Launch | Go-Live | Run go-live readiness review | Review cutover readiness, dependencies, and final launch risk tracker. | Pammi Gaur |  | High | Not Started |  | 2026-07-01 | 2026-07-05 |  | 7 | [6 empty] | Start the launch readiness meeting pack. | 2026-06-27 |  |  |  | July go-live checkpoint. | Implementation Plan
| Board Reporting | Automation | Automate monthly board deck checks | Automate data validations and QA checks before board deck publication. | Pankaj Vairagade |  | Critical | On Hold |  | 2026-07-06 | 2026-07-15 |  | 15 | 3 | [5 empty] | Resume once data source mapping is approved. | 2026-07-04 |  |  |  | Paused pending upstream data mapping. | Quality Check
Formulas:
Days Open = IF([Planned Start]="","",IF([Completed Date]<>"",[Completed Date]-[Planned Start],TODAY()-[Planned Start]))
Overdue Flag = IF(OR([Due Date]="",[Status]="Completed",[Status]="Cancelled"),"",IF(AND([Due Date]<TODAY(),[Status]<>"Completed",[Status]<>"Cancelled"),"Overdue","On Track"))

## Task_Steps
Task Steps
Enter Parent Task ID for each step. Project, source, employee, status, and manager mapping pull automatically from Task_Tracker.
Step ID | Parent Task ID | Parent Task Title | Parent Project | Step Name | Step Description | Step Owner | Step Status | Action Type | Planned Date | Due Date | Completed Date | Est. Hours | Actual Hours | Hours Variance | Days Open | Overdue | Notes | Parent Source | Parent Manager | Parent Employee | Parent Task Status | Project Key | Step Month Bucket | Manager Report
| TSK-0001 |  |  | Gather kickoff notes | Collect client and internal kickoff requirements. | Pammi Gaur | Completed |  | 2026-04-01 | 2026-04-02 | 2026-04-01 | 3 | 3 |  |  |  | Kickoff notes documented.
| TSK-0001 |  |  | Prepare requirement template | Draft the requirement capture template. | Pammi Gaur | Completed |  | 2026-04-01 | 2026-04-03 | 2026-04-03 | 4 | 4 |  |  |  | Template approved.
| TSK-0001 |  |  | Finalize signed scope | Close open questions and secure signoff. | Pammi Gaur | Completed |  | 2026-04-03 | 2026-04-05 | 2026-04-04 | 5 | 4 |  |  |  | Signoff received.
| TSK-0002 |  |  | Draft checklist structure | Create the first version of the onboarding checklist. | Pammi Gaur | Completed |  | 2026-04-06 | 2026-04-07 | 2026-04-07 | 3 | 3 |  |  |  | Version 1 completed.
| TSK-0002 |  |  | Review checklist with ops | Walk through checklist details with operations leads. | Pammi Gaur | In Progress |  | 2026-04-08 | 2026-04-10 |  | 4 | 2 |  |  |  | Review in progress.
| TSK-0002 |  |  | Publish final checklist | Release the final checklist after review comments. | Pammi Gaur | Not Started |  | 2026-04-10 | 2026-04-12 |  | 3 |  |  |  |  | Pending review completion.
| TSK-0003 |  |  | Identify training topics | Confirm the training modules and coverage. | Pammi Gaur | Completed |  | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2 | 2 |  |  |  | Topics confirmed.
| TSK-0003 |  |  | Send proposed schedule | Circulate the proposed training calendar. | Pammi Gaur | Review |  | 2026-04-10 | 2026-04-11 |  | 3 | 3 |  |  |  | Shared for approval.
| TSK-0003 |  |  | Confirm attendee list | Validate final attendees with client stakeholders. | Pammi Gaur | In Progress |  | 2026-04-11 | 2026-04-14 |  | 3 | 2 |  |  |  | Awaiting attendee confirmation.
| TSK-0004 |  |  | Freeze content list | Lock the website content inventory. | Pammi Gaur | Completed |  | 2026-04-03 | 2026-04-04 | 2026-04-04 | 2 | 2 |  |  |  | Content list frozen.
| TSK-0004 |  |  | Vendor approval for freeze | Obtain vendor confirmation for freeze window. | Pammi Gaur | Blocked |  | 2026-04-05 | 2026-04-08 |  | 4 | 1 |  |  |  | Vendor confirmation still pending.
| TSK-0005 |  |  | Outline readiness criteria | Define the readiness criteria for go-live. | Pammi Gaur | Not Started |  | 2026-05-01 | 2026-05-03 |  | 3 |  |  |  |  | Planned for May.
| TSK-0005 |  |  | Collect owner signoff dates | Gather owner confirmations and availability. | Pammi Gaur | Not Started |  | 2026-05-04 | 2026-05-06 |  | 2 |  |  |  |  | Not yet started.
| TSK-0005 |  |  | Publish launch checklist | Share final launch readiness checklist. | Pammi Gaur | Not Started |  | 2026-05-06 | 2026-05-08 |  | 2 |  |  |  |  | Scheduled after signoffs.
| TSK-0006 |  |  | Create defect categories | Set defect categories and severity rules. | Pankaj Vairagade | Completed |  | 2026-04-02 | 2026-04-03 | 2026-04-03 | 3 | 3 |  |  |  | Categories created.
| TSK-0006 |  |  | Add testing owner matrix | Assign owners and areas for UAT coverage. | Pankaj Vairagade | Completed |  | 2026-04-03 | 2026-04-05 | 2026-04-05 | 4 | 5 |  |  |  | Owner matrix completed.
| TSK-0006 |  |  | Share defect log template | Issue the log template to the testing team. | Pankaj Vairagade | Completed |  | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2 | 2 |  |  |  | Template published.
| TSK-0007 |  |  | Pull weekly raw metrics | Collect weekly metrics from source sheets. | Pankaj Vairagade | Completed |  | 2026-04-05 | 2026-04-07 | 2026-04-07 | 4 | 4 |  |  |  | Raw data ready.
| TSK-0007 |  |  | Build leadership view | Create the executive dashboard view. | Pankaj Vairagade | In Progress |  | 2026-04-08 | 2026-04-11 |  | 6 | 4 |  |  |  | Core dashboard under build.
| TSK-0007 |  |  | QA formulas and refresh | QA formulas and refresh process before publishing. | Pankaj Vairagade | Not Started |  | 2026-04-11 | 2026-04-15 |  | 4 | 1 |  |  |  | Initial setup done; QA pending.
| TSK-0008 |  |  | Collect policy docs | Collect current policy files and approvals. | Pankaj Vairagade | Completed |  | 2026-04-04 | 2026-04-06 | 2026-04-06 | 6 | 5 |  |  |  | Most policy documents received.
| TSK-0008 |  |  | Request legal confirmation | Follow up with legal for missing approvals. | Pankaj Vairagade | On Hold |  | 2026-04-06 | 2026-04-08 |  | 5 |  |  |  |  | Waiting on legal team.
| TSK-0008 |  |  | Assemble evidence pack | Compile final evidence pack for review. | Pankaj Vairagade | On Hold |  | 2026-04-08 | 2026-04-10 |  | 5 |  |  |  |  | Blocked until legal confirmation.
| TSK-0009 |  |  | Document current checklist | Capture the current manual control checklist. | Pankaj Vairagade | Not Started |  | 2026-04-11 | 2026-04-14 |  | 6 |  |  |  |  | Planned for later in April.
| TSK-0009 |  |  | Review automation fields | Review required fields and approval logic. | Pankaj Vairagade | Not Started |  | 2026-04-15 | 2026-04-18 |  | 6 |  |  |  |  | Awaiting kickoff.
| TSK-0009 |  |  | Configure final template | Build the automated checklist template. | Pankaj Vairagade | Not Started |  | 2026-04-18 | 2026-04-22 |  | 6 |  |  |  |  | Start after design review.
| TSK-0010 |  |  | Review old workbook tabs | Review and archive outdated workbook tabs. | Pankaj Vairagade | Completed |  | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2 | 1 |  |  |  | Old tabs reviewed.
| TSK-0010 |  |  | Remove broken formulas | Fix broken formulas and broken references. | Pankaj Vairagade | Completed |  | 2026-03-25 | 2026-03-27 | 2026-03-27 | 2 | 2 |  |  |  | Formula cleanup complete.
| TSK-0010 |  |  | Final QA and publish | Final quality check and workbook publishing. | Pankaj Vairagade | Completed |  | 2026-03-27 | 2026-03-29 | 2026-03-28 | 1 | 1 |  |  |  | Final workbook published.
|  |  |  | Compile signoff evidence | Gather UAT evidence and approval mails. | Pammi Gaur | Completed |  | 2026-05-09 | 2026-05-14 | 2026-05-13 | 3 | 3 |  |  |  | Evidence compiled.
|  |  |  | Prepare release summary | Draft final release notes and open items. | Pammi Gaur | Completed |  | 2026-05-14 | 2026-05-18 | 2026-05-18 | 3 | 4 |  |  |  | Summary shared.
|  |  |  | Obtain final signoff | Secure sponsor approval for go-live readiness. | Pammi Gaur | Completed |  | 2026-05-18 | 2026-05-20 | 2026-05-19 | 2 | 2 |  |  |  | Signoff received early.
|  |  |  | Draft cutover checklist | Prepare the version 1 cutover task list. | Pammi Gaur | Completed |  | 2026-06-01 | 2026-06-02 | 2026-06-02 | 3 | 3 |  |  |  | Version 1 ready.
|  |  |  | Review dependencies | Confirm owners, timings, and dependencies. | Pammi Gaur | In Progress |  | 2026-06-02 | 2026-06-04 |  | 4 | 1 |  |  |  | Dependency review ongoing.
|  |  |  | Finalize rollback plan | Complete rollback and escalation details. | Pammi Gaur | Not Started |  | 2026-06-04 | 2026-06-06 |  | 3 |  |  |  |  | Pending final approval.
|  |  |  | Build dashboard draft | Create the first pack with required charts. | Pankaj Vairagade | Completed |  | 2026-05-14 | 2026-05-18 | 2026-05-18 | 4 | 4 |  |  |  | Draft built.
|  |  |  | Validate audit numbers | Cross-check source data and totals. | Pankaj Vairagade | Review |  | 2026-05-18 | 2026-05-22 |  | 4 | 4 |  |  |  | Under QA review.
|  |  |  | Finalize management pack | Freeze the final version for circulation. | Pankaj Vairagade | Not Started |  | 2026-05-22 | 2026-05-25 |  | 3 | 2 |  |  |  | Awaiting comments.
|  |  |  | Collect SOP change requests | Gather updates from process owners. | Pankaj Vairagade | Not Started |  | 2026-06-03 | 2026-06-05 |  | 4 |  |  |  |  | Planned.
|  |  |  | Update SOP draft | Incorporate changes and examples. | Pankaj Vairagade | Not Started |  | 2026-06-05 | 2026-06-08 |  | 5 |  |  |  |  | Not started.
|  |  |  | Publish final SOP | Release approved SOP version 2. | Pankaj Vairagade | Not Started |  | 2026-06-08 | 2026-06-10 |  | 3 |  |  |  |  | Pending review.
|  |  |  | Collect readiness inputs | Request launch readiness updates from teams. | Pammi Gaur | Not Started |  | 2026-07-01 | 2026-07-02 |  | 2 |  |  |  |  | Planned.
|  |  |  | Review risks and mitigations | Update final risk log and owners. | Pammi Gaur | Not Started |  | 2026-07-02 | 2026-07-04 |  | 3 |  |  |  |  | Planned.
|  |  |  | Run readiness review | Conduct final go-live checkpoint meeting. | Pammi Gaur | Not Started |  | 2026-07-04 | 2026-07-05 |  | 2 |  |  |  |  | Planned.
|  |  |  | Map board data sources | Finalize mapping to source systems. | Pankaj Vairagade | Completed |  | 2026-07-06 | 2026-07-08 | 2026-07-08 | 3 | 3 |  |  |  | Initial mapping done.
|  |  |  | Build QA rules | Create automated validation checks. | Pankaj Vairagade | On Hold |  | 2026-07-08 | 2026-07-12 |  | 6 |  |  |  |  | Paused.
|  |  |  | Pilot monthly run | Test the automation with one board cycle. | Pankaj Vairagade | Not Started |  | 2026-07-12 | 2026-07-15 |  | 6 |  |  |  |  | Waiting for unblock.
Formulas:
Days Open = IF([Planned Date]="","",IF([Completed Date]<>"",[Completed Date]-[Planned Date],TODAY()-[Planned Date]))
Overdue = IF(OR([Due Date]="",[Step Status]="Completed",[Step Status]="Cancelled"),"",IF(AND([Due Date]<TODAY(),[Step Status]<>"Completed",[Step Status]<>"Cancelled"),"Overdue","On Track"))

## Employee_Summary
Employee Summary
Automatic employee performance view based on Task_Tracker data.
Emp ID | Employee Name | Department | Role | Manager | Weekly Capacity | Status | Total Tasks | Open Tasks | Completed Tasks | Completion % | Est. Hrs | Actual Hrs | Variance | Overdue Tasks | This Month Tasks | This Month Hrs | This Month Utilization %
Formulas:
This Month Tasks = IF([Employee Name]="","",COUNTIFS(Task_Tracker!$F5:F1004,[Employee Name],Task_Tracker!$S5:S1004,TEXT(TODAY(),"yyyy-mm")))
This Month Hrs = IF([Employee Name]="","",SUMIFS(Task_Tracker!$O5:O1004,Task_Tracker!$F5:F1004,[Employee Name],Task_Tracker!$S5:S1004,TEXT(TODAY(),"yyyy-mm")))

## Employee_Report
Employee Report
This report now pulls task details directly from Task_Tracker and step details directly from Task_Steps. Hours and status update automatically.
Selected Employee | Pammi Gaur |  | Department |  |  | Role |  |  | Manager
Month Filter | All |  | Capacity / Week
Total Tasks |  | Open Tasks |  | Completed |  | Overdue |  | Est. Hours |  | Actual Hours
Step Count |  | Open Steps |  | Completed Steps |  | Step Actual Hrs |  | Tasks w/ Source |  | To Manager
Task Detail (Direct from Task_Tracker)
Task ID | Source | Project | Task Title | Status | Priority | Due Date | Actual Hrs | Open Steps | Linked Step IDs | Next Step | Manager
Month-wise Summary | [7 empty] | Tip
Month Start | Month | Tasks Due | Completed | Carry Forward | Actual Hrs | Open in Bucket | Completion % | Task and step sections are linked to Task_Tracker and Task_Steps. Change only the source sheets; reports update automatically.
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Current Open / Upcoming Tasks (Direct from Task_Tracker)
Task ID | Source | Project | Task Title | Status | Priority | Due Date | Actual Hrs | Next Step | Manager | Notes
Task Step Detail (Direct from Task_Steps)
Step ID | Parent Task ID | Source | Project | Step Name | Step Status | Due Date | Actual Hrs | Parent Task Status | Manager
Formulas:
Open Tasks = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1))
Task Title = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1),Task_Tracker!$I5:I1004,"Completed")
Priority = SUMIFS(Task_Tracker!$O5:O1004,Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1))
Overdue = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1),Task_Tracker!$I5:I1004,"<>Completed",Task_Tracker!$I5:I1004,"<>Cancelled")

## Manager_Report
Manager Report
This sheet updates automatically for the manager based on Task_Tracker and Task_Steps. It is meant for direct monthly review.
Selected Manager |  |  | Total Team Members |  |  | Task Source Coverage |  |  | Month
Month Filter | All |  | Manager View | This manager report updates from Task_Tracker and Task_Steps.
Total Tasks |  | Open Tasks |  | Completed |  | Overdue |  | Task Hrs |  | Step Hrs
Total Steps |  | Open Steps |  | Completed Steps |  | Tasks to Report |  | Unique Sources |  | Carry Forward
Manager Task Detail
Task ID | Employee | Source | Project | Task Title | Status | Due Date | Actual Hrs | Linked Step IDs | Open Steps | Manager Report | Notes
Month-wise Manager Summary | [7 empty] | Tip
Month Start | Month | Tasks Due | Completed | Carry Forward | Task Hrs | Open in Bucket | Completion % | This section shows month-wise counts for all tasks under the selected manager. Use Month Filter on B5 for the detail tables.
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Current Open Tasks for Manager
Task ID | Employee | Source | Project | Task Title | Status | Due Date | Actual Hrs | Next Step | Open Steps | Notes
Manager Step Detail
Step ID | Employee | Parent Task ID | Source | Project | Step Name | Step Status | Due Date | Actual Hrs | Parent Task Status | Manager
Formulas:
Open Tasks = COUNTIFS(Task_Tracker!$AB5:AB1004,B4,Task_Tracker!$L5:L1004,">="&[Month Filter],Task_Tracker!$L5:L1004,"<"&EDATE([Month Filter],1))
Manager View = COUNTIFS(Task_Tracker!$AB5:AB1004,B4,Task_Tracker!$L5:L1004,">="&[Month Filter],Task_Tracker!$L5:L1004,"<"&EDATE([Month Filter],1),Task_Tracker!$I5:I1004,"Completed")
Status = SUMIFS(Task_Tracker!$O5:O1004,Task_Tracker!$AB5:AB1004,B4,Task_Tracker!$L5:L1004,">="&[Month Filter],Task_Tracker!$L5:L1004,"<"&EDATE([Month Filter],1))
Overdue = COUNTIFS(Task_Tracker!$AB5:AB1004,B4,Task_Tracker!$L5:L1004,">="&[Month Filter],Task_Tracker!$L5:L1004,"<"&EDATE([Month Filter],1),Task_Tracker!$I5:I1004,"<>Completed",Task_Tracker!$I5:I1004,"<>Cancelled")

## Action_Status_Map
Status to Action Mapping
Edit this sheet if you want to change default action types or progress percentages.
Status | Auto-filled Action Type | Default Progress % | Notes
Not Started | Plan | 0% | Task has not started yet
In Progress | Execute | 50% | Task is actively being worked on
Review | Review | 80% | Waiting for QA/review/approval
On Hold | Wait | 20% | Paused pending input or dependency
Blocked | Escalate | 30% | Needs intervention or unblocker
Completed | Close | 100% | Task finished
Cancelled | Cancel | 100% | Task closed without completion

## Monthly_Template
Monthly Report Template
Change B4 to any month start date (for example 01-Apr-2026) to generate a reusable monthly report view.
Reporting Month | 2026-04-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Apr_2026
Monthly Report - April 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-04-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## May_2026
Monthly Report - May 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-05-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Jun_2026
Monthly Report - June 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-06-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Jul_2026
Monthly Report - July 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-07-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Aug_2026
Monthly Report - August 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-08-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Sep_2026
Monthly Report - September 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-09-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Oct_2026
Monthly Report - October 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-10-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Nov_2026
Monthly Report - November 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-11-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Dec_2026
Monthly Report - December 2026
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2026-12-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Jan_2027
Monthly Report - January 2027
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2027-01-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Feb_2027
Monthly Report - February 2027
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2027-02-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Mar_2027
Monthly Report - March 2027
Tasks are entered only in Task_Tracker. This month tab summarizes tasks due in the month and shows all unfinished older tasks as carry forward.
Reporting Month | 2027-03-01 |  | Month Code |  |  | Carry-forward rule | Open tasks with due dates before this month automatically appear in Carry Forward.
Tasks Due This Month |  |  | Completed in Bucket |  |  | Carry Forward Open |  |  | Actual Hours in Bucket
Employee Summary | [8 empty] | How to use
Employee | Department | Tasks Due | Completed | Open in Bucket | Carry Forward | Est. Hrs | Actual Hrs | Completion % | Edit tasks in Task_Tracker only. Monthly tabs are reporting views. Open prior tasks keep appearing until status becomes Completed or Cancelled.
Task Detail - Employee 1
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Task Detail - Employee 2
Tasks due in this month bucket (top 18 shown, sorted by due date).
Task ID | Project | Task Title | Status | Priority | Due Date | Completed | Act Hrs | Next Step
Carry Forward Into This Month | [8 empty] | Logic
Task ID | Assigned To | Project | Task Title | Status | Original Due Date | Actual Hrs | Next Step | Notes | These are older tasks with due dates before this month that are still open. They continue to show until their status changes to Completed or Cancelled.
Tip: for unlimited detail beyond the visible rows here, filter Task_Tracker by Due Date month or Assigned To.

## Lists (hidden)
Status | Priority | Employee Names | Task IDs | Report Months | Employee Status | YesNo | Month Codes
Not Started | Low |  |  | All | Active | Yes | 2026-04
In Progress | Medium |  |  | 2026-04 | Inactive | No | 2026-05
Review | High |  |  | 2026-05 |  |  | 2026-06
On Hold | Critical |  |  | 2026-06 |  |  | 2026-07
Blocked |  |  |  | 2026-07 |  |  | 2026-08
Completed |  |  |  | 2026-08 |  |  | 2026-09
Cancelled |  |  |  | 2026-09 |  |  | 2026-10
|  |  |  | 2026-10 |  |  | 2026-11
|  |  |  | 2026-11 |  |  | 2026-12
|  |  |  | 2026-12 |  |  | 2027-01
|  |  |  | 2027-01 |  |  | 2027-02
|  |  |  | 2027-02 |  |  | 2027-03
2027-03

## Report_Pammi_Gaur
Employee Report - Pammi Gaur
This report now pulls task details directly from Task_Tracker and step details directly from Task_Steps. Hours and status update automatically.
Selected Employee | Pammi Gaur |  | Department |  |  | Role |  |  | Manager
Month Filter | All |  | Capacity / Week
Total Tasks |  | Open Tasks |  | Completed |  | Overdue |  | Est. Hours |  | Actual Hours
Step Count |  | Open Steps |  | Completed Steps |  | Step Actual Hrs |  | Tasks w/ Source |  | To Manager
Task Detail (Direct from Task_Tracker)
Task ID | Source | Project | Task Title | Status | Priority | Due Date | Actual Hrs | Open Steps | Linked Step IDs | Next Step | Manager
Month-wise Summary | [7 empty] | Tip
Month Start | Month | Tasks Due | Completed | Carry Forward | Actual Hrs | Open in Bucket | Completion % | Task and step sections are linked to Task_Tracker and Task_Steps. Change only the source sheets; reports update automatically.
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Current Open / Upcoming Tasks (Direct from Task_Tracker)
Task ID | Source | Project | Task Title | Status | Priority | Due Date | Actual Hrs | Next Step | Manager | Notes
Task Step Detail (Direct from Task_Steps)
Step ID | Parent Task ID | Source | Project | Step Name | Step Status | Due Date | Actual Hrs | Parent Task Status | Manager
Formulas:
Open Tasks = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1))
Task Title = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1),Task_Tracker!$I5:I1004,"Completed")
Priority = SUMIFS(Task_Tracker!$O5:O1004,Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1))
Overdue = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1),Task_Tracker!$I5:I1004,"<>Completed",Task_Tracker!$I5:I1004,"<>Cancelled")

## Report_Pankaj_Vairagade
Employee Report - Pankaj Vairagade
This report now pulls task details directly from Task_Tracker and step details directly from Task_Steps. Hours and status update automatically.
Selected Employee | Pankaj Vairagade |  | Department |  |  | Role |  |  | Manager
Month Filter | All |  | Capacity / Week
Total Tasks |  | Open Tasks |  | Completed |  | Overdue |  | Est. Hours |  | Actual Hours
Step Count |  | Open Steps |  | Completed Steps |  | Step Actual Hrs |  | Tasks w/ Source |  | To Manager
Task Detail (Direct from Task_Tracker)
Task ID | Source | Project | Task Title | Status | Priority | Due Date | Actual Hrs | Open Steps | Linked Step IDs | Next Step | Manager
Month-wise Summary | [7 empty] | Tip
Month Start | Month | Tasks Due | Completed | Carry Forward | Actual Hrs | Open in Bucket | Completion % | Task and step sections are linked to Task_Tracker and Task_Steps. Change only the source sheets; reports update automatically.
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Current Open / Upcoming Tasks (Direct from Task_Tracker)
Task ID | Source | Project | Task Title | Status | Priority | Due Date | Actual Hrs | Next Step | Manager | Notes
Task Step Detail (Direct from Task_Steps)
Step ID | Parent Task ID | Source | Project | Step Name | Step Status | Due Date | Actual Hrs | Parent Task Status | Manager
Formulas:
Open Tasks = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1))
Task Title = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1),Task_Tracker!$I5:I1004,"Completed")
Priority = SUMIFS(Task_Tracker!$O5:O1004,Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1))
Overdue = COUNTIFS(Task_Tracker!$F5:F1004,B4,Task_Tracker!$L5:L1004,">="&[Total Tasks],Task_Tracker!$L5:L1004,"<"&EDATE([Total Tasks],1),Task_Tracker!$I5:I1004,"<>Completed",Task_Tracker!$I5:I1004,"<>Cancelled")